## MSD
Sl. No. | Topic | Tasks | Checklist
1 | Training | MOSIP Platform Training
MOSIP Platform Demo
MOSIP Deployment Architecture
Train the trainer
Installing and configuring the registration client
Installing and configuring the biometric devices and its SBI Software
Pre-registration and Registration client operations
UIN generation and printing of the ID Card
Auth
Operator and Supervisor Training
2 | Customization Checklist | High Definition Country Flag image
High Definition Landscape backdrop image to be displayed on the Pre-registration and Registration Client screen
ID Schema definition
Master Data
Address structure
Holiday list
ID Card Design template
Temporary email ID (to b provided by MOSIP team)
Email Gateway details (decided to use MOSIP Given temporary email ID)
SMS Gateway details (Decided not use SMS for this pilot)
3 | Platform Readiness | Infra (Cloud, Hardware, Software, Devices)
Biometric Devices availability
Registration Laptops availability
Cloud Sandbox
On-Prem Infra
ABIS
Windows SDK
Server SDK
Functionality
Pre-registration
Registration
UIN generation
ID Card Printing
Auth
Biometric Auth (Fingers only)
OTP Auth
Infrastructure
Clear Kafka cache
Clear the residual packets Landing Zone (inside the pod)
Clear ActiveMQ
Backup SoftHSM keys (zip it up and share it with country team)----after the day 1 of the pilot
All client machines have wireguard access
Clear Audit Table
4 | Operations and Logistics | Registration Center
One or more registration stations where people can walk-in in order to register
Biometric devices and printer with scanner attached to the registration workstation
One or more standby registration kits
A registration operator and/or a supervisor
A print station dedicated to the printing of ID Cards
Enough space for people to be seated waiting for their turn
Tokenization mechanism for batching up people to register at various slots (for walk-in registrations only)
Handouts that may be given to people explaining the flow of activities
Posters on what can/cannot be carried inside the registration center
Pre-printed consent form to be given to people for fill up their details and signing for consent
Power backup
Security measures as deemed appropriate to guard the registration center
A large television kept in the reception area that would play videos explaining the registration process
Staff may be wearing a uniform or badge for identification purpose
A helpdesk with a dedicated person to clarify any queries
People
One trained registration operator per registration workstation
A trained supervisor
A standby registration operator
A standby supervisor
Registration Client Operations handbook printed and distributed
Registration Kit
External monitor for the residents to see
Registration Workstation
Latest Windows Update applied
Antivirus Software installed with latest update
Other applications that has nothing to do with registration client is deleted/uninstalled
Biometric Devices
Finger Print Slab Scanner is connected
IRIS scanner is connected
Face camera is connected
If the connected via hub, the hub is a powered hub
The biometric devices are registered with the vendor and are not going to expire in near time
MDS Software
MDS software is installed and running
The devices are working fine as observed from the MDS Console
Printer/Scanner
Each workstation is connected to a printer/scanner
The workstation is capable of printing/scanner - check
The printer/scanner is loaded with white papers
The printer/scanner has sufficient toner/ink
Photo Booth
White background (A stand with a white cloth)
Adjustable Focus light
The resident sitting position is marked and well adjusted with the camera
Standby registration kit is fully functional
A notepad for each registration operator to note down the RID number, name and telephone number
Printing workstation to print the ID Cards
A desk
A good configuration laptop or desktop
A printer connected to the workstation to print the ID cards
Registration Process Check List
Receive the resident and explain the process quickly
Ensure that the consent form is signed
Check the Proof of Identity and verify if the demographic data is accurate
While scanning the documents, ensure that the scanned document is legible.
Follow the best practices while collecting biometrics
Ask the resident to go through the preview page carefully
Print the acknowledgement and hand it over to the resident
Explain the contents of the registration acknowledgement slip and the need for keeping it safely
Make a manual entry in a register or a computer about the details of the registration done
Inform the resident the next steps after leaving the registration station
Inform the registration supervisor about completion of registration
Invite the next person in the queue
5 | Just before going Live (1 or 2 weeks before) | End to End Sanity testing is successful
Platform readiness - see above
Communication and Public relations
Notification to residents
Notification to support teams
Notification vendors for support
Notification to MOSIP team
Public notifications
Media
Temporary Eateries
All logistics re-checked
Posters
COVID materials such as sanitizers, masks, gloves, medicines
Emergency medicines
Ambulance near registration center ready with medical staff
Registration center fumigated
Fire safety equipment
6 | Going Live | Day 1 - Few registrations with internal staff (Controlled registration)
Observations
Troubleshooting the issues
Fixing the issues
Day 2 - Few registrations to check if the issues observed the previous day doesn’t occur again
Day 3 - Register Senior staff and Bureaucrats
Day 4 to Day N - Start registering residents
Daily reports
7 | Demographic Distribution of Registrations | Start with new Adult registrations with the following distribution
50% of Adult males
25% of Adult females
25% of Elderly
Next, register children less than 5 years old - about 5% population
Next, register adult with biometric exception - about 5% population
Best practices while collecting Biometrics
1 | Ensure biometric device is cleaned every time before capturing
2 | Show the resident how to keep the fingers on the slap scanner
3 | Help the resident gently press the fingers against the slap scanner
4 | Ensure that the IRIS binocular device is not held by the resident upside down
5 | Have multiple capture attempts till the best quality biometrics is captured
6 | While capturing photo, ensure that the face is capturing clearly with proper lighting
7 | While capturing exception biometrics, show the resident that the right biometric type is marked as exception
8 | While capturing the exception photo, make sure that the biometric exception is visibly captured

## PhilSys
Pre-Go live tests
Sl. No. | Topic | Tasks | Checklist
1 | Kubernetes Login | Ensure the tokens are not same as any of our environment and only philsys/msp/mosip support team is in control of it.
2 | Exposure to internet | Ensure all access to internet is shielded except for the VPN.
3 | Check keys in HSM | Ensure all keys are in HSM. The keys are unique and generated with clear validity
4 | Artifactory check - | Check the artifactory has the following latest jars.
auth - ?
clamav - ?
hsm - ?
idobject validator - ?
5 | Master data - | Validate the master data script is run and all zones, user, registration machine, zone mapping
6 | Configuration check | All the parameters are set as per requirement. Is this the latest configuration that was used in the dry run?
7 | Recheck on the idschema | validate the idschema and ensure that matches the approved one.
8 | First packet pass process | Create a first packet process - OSI disabled for first operator. The first operator gets the UIN. Then all other operators/supervisors are onboarded by the first operator. OSI validation is enabled.
9 | Idgenerator | Do we have the pool of UIN and VID ready
10 | Partners | ABIS onboard and certificate is correct
Print service onboarded and certificate is correct
Auth partner onboarded and certificates are correct
Resident service onboarded.
11 | Digital signature | Have we obtained the certificate from CA? If not does the counties law allow you to use your own certificate (not advisable)
12 | Grafana Alert | NOC team sets alerts on grafana for CPU, load average and memory. No system should be loaded more than 40%
13 | Backup restore test | Has the backup restore tested at least once before going live?
DB
Configuration
Minio/S3
14 | Keycloak user - Admin | Is the admin users on boarded
15 | Keycloak client id and secret | is the keycloack client id and secret configured across all the systems
16 | Keycloak roles | Are the roles mapped to the client id.
17 | Dry run | Run the full system and validate with atleast 10 to 20 packets (one with OSI disabled and all others with OSI enabled). Clear the DB after the successful run.
Clear ABIS after successful run.
Check if SMS and email notifications are going through and are proper w.r.t the template.
Check if the acknowledgement and preview pages are correctly being displayed with no loss of data
Check ID Issuance
18 | SSL certificates | Do you have the final ssl certificate configured on the nginx or LB
19 | Security clearance | Has the mosip security team cleared the setup?
20 | Operational Reports | Check if the reports are coming through for various activities performed.
Go live tests
21 | Server Start | VMs, Services, K8S
22 | Health Check | Keycloak
Minio
Postgres
HSM
ABIS
SDK
Application Services
Notification Services
Print Service
23 | Seed first user | Download Reg Client
Register “first person”
Make “first person” the operator
Register first set of operators and supervisors
Onboard operators onto other reg client machines
Monitoring List
24 | Minio Backup Check | Ensure that there is a separate backup for each day. In case of incremental backup, there should be multiple restore points by day for atleast a week.
25 | Postgres Backup Check | Ensure that there is a separate backup for each day. In case of incremental backup, there should be multiple restore points by day for atleast a week.
26 | Prometheus Sandbox Alerts for Uptime and Resource ulitization | Were any systems using excessive CPU?
Were any systems running out of RAM?
Were any systems Restarted?
Were any Kubernetes pods restarted?
ToDo: Setup alerts - automatic alerts via SMS and email (configured via say SNMP) going to key people when the system is reaching certain threshold (this can be configured via Grafana)
27 | Log Backup | Backup to be ensured before redeploying or removing VMs in the system
28 | Storage growth | Check if the storage use between minio, db and logs is growing and at what rate.
project when we will ru out of storage (if at all).
ToDo: Setup alerts for crossing storage thresholds
29 | Audit and Log Errors | Extract failures logged in audit table to analyze what has gone wrong
ToDo: Have specific queries ready
Extract failures in application logs for analysis
ToDo: Have log analysis tools, queries ready
30 | Packet Count Verification | Verify registration center figures vs RID list vs Sync logs vs Minio count
31 | Packet Age in Stage | Check if any packets are stuck in any particular stage for long.
Initiate analysis for stuck packets
32 | Rejected Packets | Rejected packet count to be found. Reasonwise count to be tracked.
Analyze reason for rejections.
Identify corrective actions
33 | Back-pressure check | Check behavior of stages where packets are stuck in large numbers and how the stage is dealing with the load.
Are additional pods needed for this stage? What will happen to the next stage?
Is any corrective action needed?
Upgrade and Patch Checklist/Process
34 | Backup | Backup the following
Configuration files
Database
Logs
ObjectStore
Docker Images
Artifactory used for dependencies
35 | Health Check | Perform a health check and see if all services are running as expected. See if the upgrade changes are reflected.

## Production Hardening
Sl. No. | Topic | Tasks | Checklist
1 | Module properties | Change log level to INFO in application properties.
Disable registration processor External Stage if not required.
Reprocessor cronjob frequency and other settings
All cronjobs timings according to the country (check property files).
Disable '111111' default OTP.
Review idschema attribute names against names in Datashare policy and Auth policy for all partner (including IDA).
Review attributes specified in 'ida-zero-knowledge-unencrypted-credential-attributes'
Review id-authentication-mapping.json` in config vis-a-vis attribute names in idschema
Kafka: disable option to delete a topic: deleteTopicEnable: false (this is set while installing kafka)
2 | Backup | Set up backup for Longhorn.
Backup of Postgres db.
Replication factor in Minio.
3 | Cluster hardening | On-prem K8s cluster production configuration.
4 | Archival | Archival of logs: Since logs data grows at a rapid pace, the data needs to be achived frequently. Set up an archival process
5 | Keycloak | Keycloak Realm connection timeout settings - review all.
Valid urls redirect in Keycloak - set specific urls.
6 | Postgres | Postgres production configuration
Backup
Secure admin password
7 | Access control | Multi-factor authentication for Rancher and Keycloak.
8 | Cluster setup | Review all Wireguard keys. Are all keys accounted for? Do the machines with Wireguard keys have sufficient protection - like firewalls, password/biometric login etc.
Are correct cluster roles assigned to users in Rancher? Is RBAC set properly?
Do the users of Rancher have strong passwords only known to them?
Is Rancher and Keycloak accessible only on Wireguard and not on public net?
Who holds the Keycloak Admin credentials? Are the credentials secure?
Any stray passwords lying on the disks?
Increase the number of nodes in the cluster according to expected load.
Set rate control (throttling) parameters for PreReg.
Scripts to clean up processed packets in landing zone.
Review pod replication factors for all modules. E.g ClamAV
9 | Persistence | Enable persistence in all modules. On cloud change the storage class from 'Delete' to 'Retain'. If you already have PV as 'Delete', you can edit the PV config and change it to 'Retain' (without having to change storage class).
Make sure storage class allows expansion of storage.
allowVolumeExpansion: true
Review size of persistent volumes and update.
Increase MinIO persistent volume size based on your estimations.
Review production settings of Longhorn.